## Jira Backlog
Issue Type | Story ID | Title | Description | Story Points | Assigned To | Branch Name | Sprint
Epic | EP-1 | User Management Module | Complete user registration and face dataset handling | 13 | Pawan Sharma | feature/user-management | Sprint 1
Story | US-1 | User Registration UI | Create registration form UI using Flask templates | 5 | Rahul Verma | feature/register-ui | Sprint 1
Story | US-2 | Capture Face Dataset | Capture 20-50 face images using OpenCV | 8 | Ankit Singh | feature/face-capture | Sprint 1
Story | US-3 | Generate FaceNet Embeddings | Generate embeddings using FaceNet model | 8 | Priya Sharma | feature/facenet-embedding | Sprint 1
Epic | EP-2 | Face Recognition Module | Real-time recognition system | 21 | Pawan Sharma | feature/face-recognition | Sprint 2
Story | US-4 | Face Detection | Implement face detection using OpenCV/MTCNN | 5 | Rahul Verma | feature/face-detection | Sprint 2
Story | US-5 | Embedding Comparison | Cosine similarity matching logic | 8 | Ankit Singh | feature/embedding-match | Sprint 2
Story | US-6 | Attendance Auto Marking | Mark attendance if face matches threshold | 5 | Priya Sharma | feature/attendance-marking | Sprint 2
Epic | EP-3 | Admin Dashboard | Admin monitoring and reporting module | 13 | Pawan Sharma | feature/admin-dashboard | Sprint 3
Story | US-7 | Admin Login | Implement secure admin login | 3 | Rahul Verma | feature/admin-login | Sprint 3
Story | US-8 | View Attendance Records | Display date-wise attendance list | 5 | Ankit Singh | feature/view-attendance | Sprint 3
Story | US-9 | Export Attendance | Export attendance in CSV/Excel format | 3 | Priya Sharma | feature/export-attendance | Sprint 3
Story | US-10 | Deploy on Render | Configure deployment with gunicorn and requirements | 5 | Pawan Sharma | feature/deployment-render | Sprint 4